## Giorgos Stefanis
To-do list
To be completed by: |  |  |  | Giorgos Stefanis
Deadline: |  |  |  | Due Date: 10/26/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Group Meeting | 2025-10-20 | 2025-10-20 | 2025-10-20 | 1day | Initial video call held
100% | Started To-do list | 2025-10-21 | 2025-10-21 | 2025-10-21 | 0.5 day | Started To-do list
100% | Solving SQLNoir Cases | 2025-10-21 | 2025-10-21 | 2025-10-21 | 1 day | Complete Reading chapters
100% | Planning | 2025-10-21 | 2025-10-21 | 2025-10-21 | 0.5 day | Initial planning
100% | Technology preparation | 2025-10-22 | 2025-10-22 | 2025-10-22 | 1day | Database connection configuration
100% | Write Cases 1-4 | 2025-10-23 | 2025-10-23 | 2025-10-24 | 1 day | Cases drafted
100% | Write Cases 5-7 and choose 5 | 2025-10-24 | 2025-10-24 | 2025-10-24 | 1 day | Cases drafted
100% | Group Meeting with Ridhwan Ibrahim | 2025-10-26 | 2026-10-24 | 2025-10-26 | 0.5day | Recording and presenting each other's cases
100% | Finalize to-do list | 2025-10-22 | 2026-10-24 | 2025-10-26 | 0.5 day | Finalized to-do list
50% | Submit final on Github | 2025-10-24 | 2026-10-24 | 2025-10-26 | 1days | All requirements are uploaded on github

## Michael cipriani
To-do list
To be completed by: |  |  |  | Name Michael Cipriani
Deadline: |  |  |  | Due Date: 10/26/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Group Meeting | 2025-10-20 | 2025-10-20 | 2025-10-20 | 1 days | Initial video call held
100% | Reading/Reviewing Chapters | 2025-10-21 | 2025-10-21 | 2025-10-21 | 0.5 days | Complete Reading chapters
100% | Planning | 2025-10-21 | 2025-10-21 | 2025-10-21 | 0.5 days | Initial planning
100% | Set up To-do list | 2025-10-22 | 2025-10-22 | 2025-10-22 | 0.5 days | Finalized to-do list
100% | Technology preperation | 2025-10-22 | 2025-10-22 | 2025-10-22 | 0.5 days | Database connection configuration
100% | Write SQL Quieres 1-4 | 2025-10-23 | 2025-10-23 | 2025-10-23 | 1 day | Queries drafted
100% | Write SQL Quieres 5-7 | 2025-10-23 | 2025-10-23 | 2025-10-23 | 1 day | Queries drafted
100% | Group Meeting with Seeram Govindan | 2025-10-24 | 2025-10-24 | 2025-10-24 | 0.5 days | Recording and presenting each other's queries
50% | Submit final on Github | 2025-10-24 | 2025-10-24 | 2025-10-24 | 0.5 days | All requirements are uploaded on github

## Seeram Govindan
To-do list
To be completed by: |  |  |  | Name Seeram Govindan
Deadline: |  |  |  | Due Date: 10/26/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Group Meeting | 2025-10-20 | 2025-10-20 | 2025-10-20 | 1day | Initial video call held
100% | Reading/Reviewing Chapters | 2025-10-21 | 2025-10-21 | 2025-10-21 | .2day | Complete Reading chapters
100% | Planning | 2025-10-21 | 2025-10-21 | 2025-10-21 | .5day | Initial planning
100% | Set up To-do list | 2025-10-22 | 2025-10-22 | 2025-10-22 | .2day | Finalized to-do list
100% | Technology preperation | 2025-10-22 | 2025-10-22 | 2025-10-22 | 1days | Database connection configuration
100% | Write SQL Quieres 1-4 | 2025-10-23 | 2025-10-23 | 2025-10-23 | .5day | Queries drafted
100% | Write SQL Quieres 5-7 | 2025-10-23 | 2025-10-23 | 2025-10-23 | .2day | Queries drafted
100% | Group Meeting with Michael cipriani | 2025-10-24 | 2025-10-24 | 2025-10-24 | .5day | Recording and presenting each other's queries
50% | Submit final on Github | 2025-10-24 | 2025-10-29 | 2025-10-24 | 1days | All requirements are uploaded on github

## Youlun Wang
To-do list
To be completed by: |  |  |  | Name: Youlun Wang
Deadline: |  |  |  | Due Date: 10/26/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Group Meeting | 2025-10-20 | 2025-10-20 | 2025-10-20 | 1day | Initial video call held
100% | Started To-do list | 2025-10-21 | 2025-10-21 | 2025-10-21 | 0.5 day | Started To-do list
100% | Solving SQLNoir Cases | 2025-10-21 | 2025-10-21 | 2025-10-21 | 1 day | Complete Reading chapters
100% | Planning | 2025-10-21 | 2025-10-21 | 2025-10-21 | .5day | Initial planning
100% | Technology preparation | 2025-10-22 | 2025-10-22 | 2025-10-22 | 1days | Database connection configuration
100% | Write Cases 1-4 | 2025-10-23 | 2025-10-24 | 2025-10-24 | 1days | Cases drafted
100% | Write Cases 5-7 and choose 5 | 2025-10-24 | 2026-10-24 | 2025-10-25 | 1days | Cases drafted
100% | Finalize to-do list | 2026-10-24 | 2026-10-24 | 2025-10-26 | 0.5 day | Finalized to-do list
100% | Group Meeting with Hasan Husseini | 2026-10-24 | 2026-10-24 | 2025-10-26 | .5day | Recording and presenting each other's cases
100% | Submit final on Github | 2026-10-24 | 2026-10-24 | 2025-10-26 | 1days | All requirements are uploaded on github

## Hasan Husseini
To-do list
To be completed by: |  |  |  | Name: Hasan Husseini
Deadline: |  |  |  | Due Date: 10/26/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Group Meeting | 2025-10-20 | 2025-10-20 | 2025-10-20 | 1day | Initial video call held
100% | Started To-do list | 2025-10-21 | 2025-10-21 | 2025-10-21 | 0.5 day | Started To-do list
100% | Solving SQLNoir Cases | 2025-10-21 | 2025-10-21 | 2025-10-21 | 1 day | Complete Reading chapters
100% | Planning | 2025-10-21 | 2025-10-21 | 2025-10-21 | .5day | Initial planning
100% | Technology preparation | 2025-10-22 | 2025-10-22 | 2025-10-22 | 1days | Database connection configuration
100% | Write Cases 1-4 | 2025-10-23 | 2025-10-24 | 2025-10-24 | 1days | Cases drafted
100% | Write Cases 5-7 and choose 5 | 2025-10-24 | 2026-10-24 | 2025-10-25 | 1days | Cases drafted
100% | Finalize to-do list | 2026-10-24 | 2026-10-24 | 2025-10-26 | 0.5 day | Finalized to-do list
100% | Group Meeting with Youlun Wang | 2026-10-24 | 2026-10-24 | 2025-10-26 | .5day | Recording and presenting each other's cases
100% | Submit final on Github | 2026-10-24 | 2026-10-24 | 2025-10-26 | 1days | All requirements are uploaded on github

## Ridhwan Ibrahim
To-do list
To be completed by: |  |  |  | Name: Ridhwan Ibrahim
Deadline: |  |  |  | Due Date: 10/26/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Group Meeting | 2025-10-20 | 2025-10-20 | 2025-10-20 | 1day | Initial video call held
100% | Started To-do list | 2025-10-21 | 2025-10-21 | 2025-10-21 | 0.5 day | Started To-do list
100% | Solving SQLNoir Cases | 2025-10-21 | 2025-10-21 | 2025-10-21 | 1 day | Complete Reading chapters
100% | Planning | 2025-10-21 | 2025-10-21 | 2025-10-21 | .5day | Initial planning
100% | Technology preparation | 2025-10-22 | 2025-10-22 | 2025-10-22 | 1days | Database connection configuration
100% | Write Cases 1-4 | 2025-10-23 | 2025-10-24 | 2025-10-24 | 1days | Cases drafted
100% | Write Cases 5-7 and choose 5 | 2025-10-24 | 2025-10-25 | 2025-10-25 | 1days | Cases drafted
100% | Finalize to-do list | 2025-10-22 | 2025-10-26 | 2025-10-26 | 0.5 day | Finalized to-do list
100% | Group Meeting with Giorgos Stefanis | 2025-10-26 | 2025-10-25 | 2025-10-26 | .5day | Recording and presenting each other's cases
100% | Submit final on Github | 2025-10-26 | 2025-10-26 | 2025-10-26 | 1days | All requirements are uploaded on github